## General
Team Number: | 4
Week: | 8

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Create the input table (with either template list or our own GUI model, whichever we find works best for our purposes)
2 | Continue work on pod component
3 | Expand on our Excel file input method, add a file selector to the interface
4 | Create a addon package so that each component's code does not have to be added to Blender separately
5 | Add a "texture add" button to each component's GUI
6
7
8
B. | List dependencies or things/decision that you're waiting for in this week
1 | Meeting with Phil Barnes to discuss project details from customer perspective (Mr. Barnes is trying to find time to meet with us this week)
2
3
4
5
C. | List your accomplishments from the previous week
1 | Fixed a couple bugs that we learned about in preparing for our latest presentation (object reseting position on update and input validation)
2 | Updated website pictures to match latest release
3 | Implemented updated code that Barnes's has supplied that simplifies end constraints for parametric cubic splines
4
5
6
7
8

## Risk
Top Project Risks as of 10/29/2014
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Unsure of geometry specifications for future components | Meet with Barnes to discuss preferred specifications for future components
2
3
4

## COTS
List of third-party components being considered for use in the system as of 10/29/2014
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python
Xlrd | Library for interacting with Excel files | Python

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Generated components reset position when its parameters are changed due to how they are coded | Fix code to update position of the 3D cursor (where the object is generated) so that the object is updated into the correct coordinates
2 | Each component needs to be added to Blender separately (they are not packaged as one addon) | Make each component fall under a common type, allowing the addons fall into one "folder"
3 | There is no input validation for certain components (for example, time goes from 0 to 1, can't be negative) | Add input validation
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Reading from an Excel file means that the object cannot be modified, a new model has to be generated from the new input data | Implement the Excel reader so that updating it automatically updates the object's properties, or implement a UI list so that the table data comes from directly from Blender
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Still unsure of Blender's capability to dynamically altering data with the UIList class | UIList has't been working the way we want it too, we will look into using the old version of UIList (templateList) or our own Python GUI model for table inputs
2 | Adding textures to a component is unintuitive to for someone unfamiliar with Blender | Add a button to give a component a texture within our addon's GUI
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A