## General
Team Number: | 4
Week: | 12

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Continue documenting test cases (Update methods still need to be tested and/or documented)
2 | Work on final report
3
4
5
6
7
8
B. | List dependencies or things/decision that you're waiting for in this week
1
2
3
4
5
C. | List your accomplishments from the previous week
1 | Implement changes in wing requested by Barnes on 11/17/14
2 | Implement new parameters for parametric curves (end constraints) as requested by Barnes on 11/14/2014
3 | Implement functionality within Update method to export points back into an Excel file
4 | Create Presentation for Release 3 on 11/20/2014
5 | Fixed a minor bug in certain rotation cases
6
7
8

## Risk
Top Project Risks as of 11/26/14
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | N/A | New method to generate parametric curves takes a considerable amount of time | Look to optimize the geometry algorithm
2
3
4

## COTS
List of third-party components being considered for use in the system as of 11/26/14
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python
CSV | Library for interacting with Excel files; import and export format for spreadsheet and databases | Python

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Rotation wasn't being applied correctly for certain components | Look in the code where the conversion to euler occurs
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Generating a parametric cubic spline currently takes a considerable amount of time | Look to optimize how we generate these curves
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A