## General
Team Number: | 4
Week: | 13

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Finish documenting test cases
2 | Finish final report
3 | Create Presentation for CECS department meeting on 12/4/14
4 | Extend texture feature - current implementation allows for color only
5
6
7
8
B. | List dependencies or things/decision that you're waiting for in this week
1
2
3
4
5
C. | List your accomplishments from the previous week
1 | Completed documentation for test cases of "Update" functions
2 | Added Error dialog boxes for input validation
3 | Started final report
4
5
6
7
8

## Risk
Top Project Risks as of 12/3/14
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | New method to generate parametric curves takes a considerable amount of time | Look to optimize the geometry algorithm
2
3
4

## COTS
List of third-party components being considered for use in the system as of 12/3/14
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python
CSV | Library for interacting with Excel files; import and export format for spreadsheet and databases | Python
Add Mesh: Extra Objects | Blender Addon used to model the cross sections of components mathematically |  | Blender

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | One of the operators used to generate models involved editing an existing addon, meaning a user would have to edit this file to get our project to work correctly | Include the edited version of this file within our addon (edited parameters allowing for negative minimum and maximum values)
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Generating a parametric cubic spline currently takes a considerable amount of time | Look to optimize how we generate these curves
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A