## General
Team Number: | 4
Week: | 4

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Update cubic spline geometry to parametric cubic spline geometry (will allow for more complex shapes)
2 | Finish implementing wing specifications (only airfoil is finished, other aspects include washout, dihedral angle...)
3 | Begin implementing class for next component, fuselage
4 | Update website
5 | Begin learning the 3-D printing process regarding .stl files (as suggested by Bob Ward)
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Meeting with Phil Barnes to discuss project details from customer perspective
2
3
4
5
C. | List your accomplishments from the previous week
1 | Implemented cubic spline for airfoil geometry
2 | Updated UI to incorporate new airfoil parameters
3 | Created presentation for release 1
4 | Met with Bob Ward to demonstrate release 1 functionalities
5
6
7
8

## Risk
Top Project Risks as of 10/01/2014
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Low understanding of parametric cubic splines | Research and meet with client (Phil Barnes, engineer at Northrop Grumman)
2 | 2 | Need more knowledge on Python/Blender integration | Analyze Python class templates that come with Blender (ex. for object creation or UI)
3
4

## COTS
List of third-party components being considered for use in the system as of 10/01/2014
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | We had trouble implementing parametric cubic splines, used cubic splines instead | Finish implementing parametric cubic splines
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Currently the method that generates the airfoil creates separate panels and joins them together (this means they can't be edited after they are joined) | Implement a method for editing the object that involves unjoining the object so that each panel can have its dimensions/geometries changed then rejoining the panels
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A