## General
Team Number: | 4
Week: | 7

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Use UIList within bpy to create easy user interface to add or remove inputs
2 | Continue work on pod component
3 | Add gallery page to website to showcase components
4
5
6
7
8
B. | List dependencies or things/decision that you're waiting for in this week
1 | Meeting with Phil Barnes to discuss project details from customer perspective (Mr. Barnes has just returned from travel and we are close to finalizing a meeting time)
2
3
4
5
C. | List your accomplishments from the previous week
1 | Created a method to take in inputs from an Excel file for use in Blender
2 | Begin preparations for release 2 presentation
3 | Begin implementing class for next component, pod
4 | Finish implementing fuselage
5 | Created new website and shared with Phil Barnes and Bob Ward
6
7
8

## Risk
Top Project Risks as of 10/22/2014
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Unsure of geometry specifications for future components | Meet with Barnes to discuss preferred specifications for future components
2
3
4

## COTS
List of third-party components being considered for use in the system as of 10/22/2014
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python
Xlrd | Library for interacting with Excel files | Python

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Reading from an Excel file means that the object cannot be modified, a new model has to be generated from the new input data | Implement the Excel reader so that updating it automatically updates the object's properties, or implement a UI list so that the table data comes from directly from Blender
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Unsure of Blender's capability to dynamically altering data with the UIList class | There isn't much documentation or example of UIList implementation, we need to find out if it is possible in our case or if there are better options
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A