## General
Team Number: | 4
Week: | 9

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Finish implementing the input table
2 | Implement updated specifications for fuselage geometries (provided by Phil Barnes)
3 | Implement the "add component" UI as a dialog box, with a button to update in the properties tab
4 | Add an "add texture" button to each component's GUI
5 | Start formally documenting our test cases
6
7
8
B. | List dependencies or things/decision that you're waiting for in this week
1 | Continue work on pod component, need to finish how we'll handle tables of inputs first
2
3
4
5
C. | List your accomplishments from the previous week
1 | Expanded on our Excel file input method, added a file selector to the interface
2 | Created an addon package so that each component's code does not have to be added to Blender separately
3
4
5
6
7
8

## Risk
Top Project Risks as of 11/5/2014
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Unsure of geometry specifications for future components | Meet with Barnes to discuss preferred specifications for future components
2
3
4

## COTS
List of third-party components being considered for use in the system as of 11/5/2014
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python
Xlrd | Library for interacting with Excel files | Python

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | Certain inputs may cause a Singular matrix error | Use a try statement on the linear algebra solve call, except defaults to previous input
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | UIList (for table inputs) can be used for dynamic data, but current documentation is for materials | We would be using it for floats, not materials, find out if it is possible.
2 | Component UI (an operator) disappears when another operator is called, this means components can't be updated after another component is added | Implement the component operator as a dialog box (that just adds a default component), then have a button within the component's properties to perform updates on the geometries
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A