## General
Team Number: | 4
Week: | 2

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Translate Visual Basic code (from client) to Python to demonstrate parametric cubic spline geometry (the equations used to generate models).
2 | Determine which parts of the equations to be inputs
3 | Implement translated code into a Blender object class
4 | Design and implement UI for inputs
5 | Update Website
6
7
8
B. | List dependencies or things/decision that you waiting for in this week
1 | Meeting with Phil Barnes to discuss project details from customer perspective
2
3
4
5
C. | List your accomplishments from the previous week
1 | Project Proposal
2 | Look over VSP to see possible features to implement
3 | Met with Bob Ward for more information on project
4 | Created general UI for application within Blender
5 | Become better acquainted with Blender
6 | Learn simple Python syntax
7
8

## Risk
Top Project Risks as of 09/17/2014
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | N/ A | Low understanding of parametric cubic splines | Research and meet with client (Phil Barnes, engineer at Northrop Grumman)
2 | 1 | Need more knowledge on Python/Blender integration | Analyze Python class templates that come with Blender (ex. for object creation or UI)
3
4

## COTS
List of third-party components being considered for use in the system as of 09/17/2014
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircrafts |  | Python
Python | To create scripts that handle the editing of aircraft specifications

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Unsure of direction of project with respect to working with VSP | Communicate with Mr. Barnes to understand which direction best suits this project
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A