## General
Team Number: | 4
Week: | 10

## Progress
Progress Description:
Describe the progress on the project during the past week, both in qualitative and quantitative.
A. | List your top priority works that must be accomplished in this week
1 | Meeting with Phil Barnes on Friday
2 | Create presentation for meeting
3 | Implement CSV to read excel files
4 | Finish implementing updated specifications for fuselage geometries (provided by Phil Barnes)
5 | Input validation for new dialog box methods
6 | Continue documenting test cases
7 | Continue to work on pod component
8 | Fix file selector in dialog box
B. | List dependencies or things/decision that you're waiting for in this week
1
2
3
4
5
C. | List your accomplishments from the previous week
1 | Implement the "add component" UI as a dialog box, with a button to update in the properties tab
2 | Implemented a static update function (always stays on screen), with functionality to choose which object to edit
3 | Add an "add texture" button to each component's GUI
4 | Started formally documenting our test cases
5 | Implemented method to test for unique name identifier
6
7
8

## Risk
Top Project Risks as of 11/12/2014
Rank |  | Risk Description | Risk Mitigation Action Items
This Week | Last Week
1 | 1 | Unsure of geometry specifications for future components | Meet with Barnes to discuss preferred specifications for future components
2 | N/A | File selectors may not work with a dialog box | Research dialog box behavior
3
4

## COTS
List of third-party components being considered for use in the system as of 11/12/2014
Component Name | Function of the component in the system | Related components
|  | Dependency | Interaction
Blender | To draw the 3D aircraft |  | Python
Python | To create classes within Blender that handle the creation and modification of aircraft specifications |  | Blender
Numpy | Library for mathematic computations (specfically solving systems of equations with matrices) | Python
CSV | Library for interacting with Excel files; import and export format for spreadsheet and databases | Python

## Defects, Problems, and Concerns
Defects, Problems, and Issues
Describe the defects, problems, and issues in the project during the past week
Avoidable Defects: a shortcoming, fault, imperfection or problem that could be prevented such as human error
Unavoidable Defects: a shortcoming, fault, imperfection or problem that the team has no control over such as a change in the requirement
Concern: A matter that might cause some trouble, worry or an unsettled matter is ready for a decision
A. List any avoidable defect occurred in the previous week
| Avoidable Defects | Proposed Solution
1 | N/A | N/A
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
B. List any unavoidable defect occurred in the previous week
| Unavoidable Defects | Proposed Solution
1 | Blender has a weird naming scheme for duplicate mesh names (i.e. latest mesh is "mesh.000" instead of "mesh.001") | Implement method to handle duplicate names in our own scheme
2 | N/A | N/A
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A
C. List any concern occurred in the previous week
| Concerns | Proposed Solution
1 | Xlrd needs to be installed into Blender's Python directory, which may cause confusion for users trying to install the addon | Implement CSV for Excel reading instead, as it is automatically included in Blender's Python library
2 | Dialog box closes when attempting to open an excel file | Figure out the problem; may have to scrap dialog boxes
3 | N/A | N/A
4 | N/A | N/A
5 | N/A | N/A